## Sheet1
www.goodoldmanoj.com
Burn down chart TKPPL Bespoke Flatizen
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Presentasi Flatizen | Story 1 | Task 1.1 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Flatizen | Story 1 | Task 1.2 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Flatizen | Story 1 | Task 1.3 | 4 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Flatizen | Story 1 | Task 1.4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Flatizen | Story 1 | Task 1.5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Flatizen | Story 2 | Task 3.1 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Flatizen | Story 2 | Task 3.2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Flatizen | Story 2 | Task 3.3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Flatizen | Story 3 | Task 3.4 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 0 | 0 | 0 | 0
Presentasi Flatizen | Story 4 | Task 4.1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
Presentasi Flatizen | Story 4 | Task 4.2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
Presentasi Flatizen | Story 5 | Task 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
Ideal - Remaining efforts in uninterrupted working hours |  |  | 52 | 46.8 | 41.6 | 36.4 | 31.2 | 26 | 20.8 | 15.6 | 10.4 | 5.2 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 52 | 52 | 40 | 33 | 25 | 23 | 17 | 15 | 15 | 5 | 0
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered